## PlannedVsBurnt
Resources | Planned Effort (In Hours) | Burnt Effort (In Hours)
Yagna | 120 | 170.5
Manoz | 120 | 166
Mahesh | 120 | 109
Vijay | 120 | 147
Deva | 120 | 165

## Weekly_Effort
Resources | Week1 | Week2 | Week3 | Total
Yagna | 56 | 53.5 | 61 | 170.5
Manoz | 55 | 51 | 60 | 166
Mahesh | 49 | 27 | 33 | 109
Vijay | 50 | 47 | 50 | 147
Deva | 50 | 58 | 57 | 165
0
5 | 49
11 | 43
11 | 43
11 | 44
11 | 59
4 | 29
53 | 4.45
Note on C4: HCSC User: Sick this week for 2 days
Note on D4: HCSC User: Sick & admitted to Hospital